## Sheet1
MA1008 Project Log
Semester 2 AY2023/2024

	Work done	Issues/Difficulties	Comments
Week 0
Monday
Tuesday
Wednesday
Thursday
Friday
Saturday	Completed the math utilities and the tests for the math functions.	Inaccurate angle calculations are a massive pain.	Allowing the use of numpy as well as objects would have simplified a lot of things.
Sunday	Completed the design of the data structures.		Allowing the use of the json library would have made life easier. / Polygons, or shapes, should be a list of edges, with each edge being a dictionary that contains information about it, like the vertices being in a list, the type of edge, curved or straight, as a string property in the dictionary. / Straight edges will have 2 vertices, while curved edges will have 4. / An icon will be a list of polygons.

Week 1
Monday	Edited the convert_3d_to_2d and convert_2d_to_3d functions to be easier to work with.		Need to figure out how to convert a semicircle and a quarter circle into a bezier.
Tuesday	Completed the library to draw icons using a list of coordinates. / This also means that the data structure for the points is also well-defined now, with icons being a list of polygons, and polygons being a dictionary with 4 properties, the list of vertices (required), the fill colour (optional), the pen colour (optional) and the number of segments for bezier curves (optional). Basically, the data structures are now implemented in code. / The list of vertices is a list of points, which are just column matrices.
Wednesday	Added a pen size property to the dictionary.
Thursday	Added a function to convert all of the vertices in the dictionary to a given dimension. / Added a square root function. / Added functions to approximate a circular arc as a bezier curve.	It took days to even figure out how to approximate a circular arc as a bezier curve mathematically, writing the function took like a whole day’s worth of work.
Friday	Added a function to apply the transformations to all of the vertices in the correct order.	Just had to remember that the transformations are arranged from right to left, with the first transformation being on the right of the matrix to apply all the transformations to, instead of the usual left to right.
Saturday	Completed the function to resize the screen as required. / Added a bunch of supporting functions for that function and wrote tests for all the testable functions (functions with no side effects).	Needed to have a lot of different functions to be able to recurse properly.
Sunday

Week 2
Monday
Tuesday
Wednesday
Thursday	Started work on the UI library. / Started work on the file explorer.
Friday	Completed the file explorer.		Doing the file explorer was quite fun. / Gotta figure out the rest of the UI and interactions.
Saturday	Completed the title screen. / Improved the file explorer.		Spent way too much time on the file explorer and the title screen, have to move on to getting the rest of the UI interactions done. / Afterwards, finding the vertices for the 3 logos is going to be a massive pain and will take absolutely forever.
Sunday

Week 3
Monday	Implemented a “global” (not really) state system for the entire program so that each step of the UI can return a value.		The reason for this is that the on click and on keypress handlers can only take a callback function, which can’t return any values to the caller since it’s a handler. Hence there is a need to have some kind of global state that the program can keep track of to make sure the main program knows what to do.
Tuesday	Started work on the main menu of the UI. / Recreated the cog component of the Rust logo using beziers. / Recreated the mount component of the Rust logo using beziers.
Wednesday
Thursday	Started work on the World Bank logo.	It is extremely tedious to get all the points for the logo.
Friday	Started work on the user manual (file called README). / Added a licence, GPL V3 to be specific.
Saturday	Completed the World Bank and CERN logo.	It is extremely tedious to get all the points for the logos.	Should complete the Rust logo by tomorrow.
Sunday	Completed the Rust logo. / Also fixed a bug in the function to approximate circular arcs as beziers, which was due to the function getting the tangent vector of the wrong vector.		This logo was much easier to do, since the majority of the logo could be created by rotating one object around the origin by a specific angle until a full circle was obtained. It’s really quite fitting that a logo for a programming language is easy to programmatically create.

Week 4
Monday
Tuesday
Wednesday	Completed the library to save files.
Thursday	The user manual (file called README) is mostly complete. / Continued work on the main menu.	UI code is very, very, very boring to write. It is the same thing over and over and over again.
Friday	Switched the step system for a function call stack instead.		The function stack is far more manageable and more intuitive. Each function that calls a UI component can simply push the callback function to the function stack and the function will be executed once the UI component is closed. / The steps system would have been far more convoluted and difficult to work with, as the UI isn’t a single line, but rather a mess of connections between all the different prompts, which would have been absolutely insane to keep track of using the steps system.
Saturday	Completed the main menu. / Fixed a bunch of bugs.	The file containing the main menu is absolutely massive, which makes it pretty difficult to work with. Even then, the file cannot be split up as each function and prompt of the main menu is all interconnected, which will result in circular import errors if the functions in the main menu file were split up. / Having to propagate the options through every single function in the main menu file wasn’t fun either, but since objects weren’t allowed (you need the class construct to create custom objects), this is what you have to do. Wait but what about dictionaries? There is no type checking or validation when using dictionary keys, and since the keys are a string, the names aren’t checked either. Using a function parameter at least allows for type checking and name checking, which is much better, even if it is painful to propagate the options through every single function. / Maybe I should have used a named tuple for the options, but it’s too late for that now.
Sunday	Ironed out a few behaviours and polished up the program.		The program is pretty much complete.